GUILD OS

Technical Roadmap & Build Plan

ARCHITECTURE  ·  STACK  ·  DATABASE  ·  API  ·  SPRINT PLAN

February 2026  |  v1.0

CONFIDENTIAL

# 1. Architecture Overview

ARCHITECTURE PRINCIPLE Website-first, Discord-native. The web app is the brain (dashboards, analytics, reputation, coordination). The Discord bot is the nervous system (data collection, notifications, commands). Both talk to the same backend. A PWA wrapper gives mobile access with zero native app development.

## 1.1 System Architecture

HIGH-LEVEL ARCHITECTURE ┌─────────────────────────────────────────────────────────────────┐ │ GUILD OS PLATFORM │ ├─────────────────────────────────────────────────────────────────┤ │ CLIENTS │ │ ┌──────────────┐ ┌──────────────┐ ┌──────────────┐ │ │ │ Web App │ │ Mobile PWA │ │ Discord Bot │ │ │ │ (Next.js) │ │ (PWA) │ │ (Discord.js) │ │ │ └───────┬──────┘ └──────┬───────┘ └──────┬───────┘ │ ├────────┴────────────┴────────────┴───────────────────────────┤ │ API GATEWAY (Next.js API Routes / tRPC) │ ├─────────────────────────────────────────────────────────────────┤ │ SERVICES │ │ ┌───────────┐ ┌───────────┐ ┌───────────┐ ┌────────────┐ │ │ │ Reputation│ │ Analytics │ │ Events │ │ AI Advisor │ │ │ │ Service │ │ Service │ │ Service │ │ Service │ │ │ └─────┬─────┘ └─────┬─────┘ └─────┬─────┘ └──────┬─────┘ │ ├──────┴──────────┴──────────┴────────────┴─────────────────────┤ │ DATA LAYER │ │ ┌───────────┐ ┌───────────┐ ┌───────────┐ ┌────────────┐ │ │ │ Postgres │ │ Redis │ │ S3/R2 │ │ Timescale │ │ │ │ (primary) │ │ (cache) │ │ (files) │ │ (metrics) │ │ │ └───────────┘ └───────────┘ └───────────┘ └────────────┘ │ └─────────────────────────────────────────────────────────────────┘

## 1.2 Why This Architecture

This is a monorepo, full-stack TypeScript architecture. One language everywhere — frontend, backend, Discord bot, shared types. Here’s the reasoning behind each decision:

| Decision | Choice | Why |
| --- | --- | --- |
| Framework | Next.js 14+ (App Router) | SSR for SEO (reputation profiles), API routes eliminate separate backend, Vercel deployment = zero DevOps |
| Language | TypeScript everywhere | Shared types between frontend, backend, and Discord bot. One language = faster iteration with AI coding agents |
| Database | PostgreSQL (Supabase) | Relational data (users, guilds, events), built-in auth, real-time subscriptions, generous free tier, Row Level Security |
| ORM | Drizzle ORM | Type-safe, lightweight, SQL-like syntax. Better DX than Prisma for complex queries. Faster builds. |
| Cache | Redis (Upstash) | Session management, rate limiting, real-time leaderboards, pub/sub for live updates. Serverless Redis = no infrastructure management |
| Real-time | Supabase Realtime + Pusher | Supabase for DB-driven updates (new contributions), Pusher for event-driven (rally alerts, live coordination) |
| Auth | Supabase Auth + Discord OAuth | Discord OAuth is mandatory (our users live on Discord). Supabase Auth handles sessions, tokens, and role management |
| AI | Claude API (Anthropic) | Best reasoning for strategic advice. Structured outputs for data extraction. Cost-effective for the query volume we expect |
| File Storage | Cloudflare R2 | S3-compatible, zero egress fees. Screenshots, profile images, exported reports |
| Hosting | Vercel (web) + Railway (bot) | Vercel: zero-config Next.js deployment, edge functions, preview deploys. Railway: persistent process for Discord bot |
| Styling | Tailwind CSS + shadcn/ui | Utility-first CSS for rapid prototyping. shadcn/ui for production-quality components without vendor lock-in |
| Monorepo | Turborepo | Shared packages (types, utils, DB schema) across web app, Discord bot, and future mobile app. Cached builds. |
| Time Series | TimescaleDB (on Supabase) | Contribution metrics over time, engagement trends, reputation score history. PostgreSQL extension = no separate service |

# 2. Project Structure

MONOREPO LAYOUT (Turborepo) guild-os/ ├── apps/ │ ├── web/ # Next.js web application │ │ ├── app/ # App Router pages │ │ │ ├── (marketing)/ # Landing, pricing, blog │ │ │ ├── (dashboard)/ # Authenticated guild views │ │ │ ├── (profiles)/ # Public reputation profiles │ │ │ └── api/ # API routes (tRPC) │ │ ├── components/ # React components │ │ └── lib/ # Client utilities │ │ │ └── bot/ # Discord bot │ ├── commands/ # Slash commands │ ├── events/ # Discord event handlers │ ├── services/ # Bot business logic │ └── index.ts # Bot entry point │ ├── packages/ │ ├── db/ # Drizzle schema + migrations │ │ ├── schema/ # Table definitions │ │ ├── migrations/ # SQL migrations │ │ └── seed/ # Dev seed data │ ├── types/ # Shared TypeScript types │ ├── utils/ # Shared utilities │ ├── reputation/ # Reputation scoring engine │ └── ai/ # AI advisor service layer │ ├── turbo.json # Turborepo config ├── package.json # Root package.json └── .env.example # Environment variables

## 2.1 Key Design Principles

- Shared types, zero drift: The packages/types directory defines every entity (Guild, Member, Event, ReputationScore) once. Both the web app and Discord bot import from the same source. No desynchronization.

- Database as single source of truth: The packages/db directory owns the schema. Both apps read/write through the same Drizzle client. No data duplication between web and bot.

- Reputation as a library: The scoring engine lives in packages/reputation as a pure-function library. It takes contribution data in, returns reputation scores out. Testable in isolation. Importable from anywhere.

- AI as a service: The packages/ai directory wraps the Claude API with game-specific prompts, context management, and response parsing. Both the web app and bot can call the AI advisor through the same interface.

# 3. Database Schema

The database is designed around five core domains: Identity, Guilds, Contributions, Events, and Reputation. All tables use UUIDs as primary keys and include created_at/updated_at timestamps.

## 3.1 Core Tables

IDENTITY DOMAIN users id UUID PRIMARY KEY discord_id TEXT UNIQUE NOT NULL discord_name TEXT NOT NULL avatar_url TEXT email TEXT created_at TIMESTAMPTZ DEFAULT NOW() user_game_profiles id UUID PRIMARY KEY user_id UUID REFERENCES users game ENUM('gotc','rok','lords_mobile','eve') in_game_name TEXT NOT NULL in_game_id TEXT power_level BIGINT keep_level INTEGER last_synced TIMESTAMPTZ UNIQUE(user_id, game)

GUILD DOMAIN guilds id UUID PRIMARY KEY name TEXT NOT NULL game ENUM('gotc','rok','lords_mobile','eve') discord_server TEXT tier ENUM('free','pro','elite') DEFAULT 'free' max_members INTEGER DEFAULT 30 settings JSONB DEFAULT '{}' created_at TIMESTAMPTZ DEFAULT NOW() guild_members id UUID PRIMARY KEY guild_id UUID REFERENCES guilds user_id UUID REFERENCES users role ENUM('r1','r2','r3','r4','r5') DEFAULT 'r1' joined_at TIMESTAMPTZ DEFAULT NOW() is_active BOOLEAN DEFAULT true UNIQUE(guild_id, user_id)

CONTRIBUTION DOMAIN (TimescaleDB hypertable) contributions id UUID PRIMARY KEY guild_id UUID REFERENCES guilds user_id UUID REFERENCES users type ENUM('rally','donation','defense','event', 'scout','recruitment','diplomacy') value INTEGER NOT NULL metadata JSONB DEFAULT '{}' verified_by UUID REFERENCES users -- officer verification recorded_at TIMESTAMPTZ DEFAULT NOW() -- Hypertable for time-series queries SELECT create_hypertable('contributions', 'recorded_at');

EVENT DOMAIN events id UUID PRIMARY KEY guild_id UUID REFERENCES guilds type ENUM('rally','kvk','conquest','migration', 'custom') title TEXT NOT NULL description TEXT starts_at TIMESTAMPTZ NOT NULL ends_at TIMESTAMPTZ status ENUM('planned','active','completed','cancelled') config JSONB DEFAULT '{}' created_by UUID REFERENCES users event_signups id UUID PRIMARY KEY event_id UUID REFERENCES events user_id UUID REFERENCES users status ENUM('confirmed','tentative','declined') troop_commit JSONB -- {infantry: 50000, cavalry: 30000} signed_up_at TIMESTAMPTZ DEFAULT NOW()

REPUTATION DOMAIN reputation_scores id UUID PRIMARY KEY user_id UUID REFERENCES users game ENUM('gotc','rok','lords_mobile','eve','global') contribution DECIMAL(5,2) DEFAULT 0 -- 0-100 leadership DECIMAL(5,2) DEFAULT 0 -- 0-100 reliability DECIMAL(5,2) DEFAULT 0 -- 0-100 overall DECIMAL(5,2) DEFAULT 0 -- weighted composite updated_at TIMESTAMPTZ DEFAULT NOW() UNIQUE(user_id, game) reputation_history -- TimescaleDB hypertable user_id UUID REFERENCES users game TEXT overall DECIMAL(5,2) recorded_at TIMESTAMPTZ DEFAULT NOW() endorsements id UUID PRIMARY KEY from_user UUID REFERENCES users to_user UUID REFERENCES users skill ENUM('leadership','strategy','loyalty', 'generosity','reliability') comment TEXT created_at TIMESTAMPTZ DEFAULT NOW() UNIQUE(from_user, to_user, skill)

DIPLOMACY DOMAIN nap_agreements id UUID PRIMARY KEY guild_a UUID REFERENCES guilds guild_b UUID REFERENCES guilds status ENUM('proposed','active','expired','broken') terms TEXT starts_at TIMESTAMPTZ expires_at TIMESTAMPTZ signed_by_a UUID REFERENCES users signed_by_b UUID REFERENCES users diplomatic_messages id UUID PRIMARY KEY channel_id UUID -- virtual diplomacy channel from_guild UUID REFERENCES guilds from_user UUID REFERENCES users content TEXT ENCRYPTED sent_at TIMESTAMPTZ DEFAULT NOW()

# 4. API Design

The API uses tRPC for type-safe, auto-generated endpoints shared between the web app and Discord bot. Every procedure has built-in auth checks, rate limiting, and input validation via Zod schemas.

## 4.1 API Router Structure

tRPC ROUTER MAP appRouter ├── auth │ ├── discordCallback # OAuth flow completion │ ├── getSession # Current user session │ └── logout # End session │ ├── guilds │ ├── create # Create new guild │ ├── get # Get guild details │ ├── list # List user's guilds │ ├── members.list # Guild member roster │ ├── members.invite # Generate invite link │ ├── members.updateRole # Change member rank │ ├── settings.update # Guild configuration │ └── analytics.overview # Guild health dashboard │ ├── contributions │ ├── record # Log a contribution │ ├── batchRecord # Bulk log (officer entry) │ ├── verify # Officer verification │ ├── memberStats # Individual member stats │ ├── guildStats # Aggregate guild stats │ └── leaderboard # Contribution rankings │ ├── events │ ├── create # Schedule event │ ├── list # Upcoming events │ ├── signup # RSVP for event │ ├── updateStatus # Start/end/cancel │ └── results # Post-event summary │ ├── reputation │ ├── getProfile # Public reputation card │ ├── getHistory # Score over time │ ├── endorse # Endorse another player │ └── search # Find players by rep │ ├── diplomacy │ ├── proposeNap # Propose NAP agreement │ ├── signNap # Accept/sign NAP │ ├── listAgreements # Active agreements │ └── sendMessage # Diplomatic channel msg │ └── ai ├── askAdvisor # Strategic question ├── analyzeComposition # Troop comp analysis ├── generateReport # Post-event AI report └── parseScreenshot # OCR game screenshot

## 4.2 Discord Bot Commands

| Command | Description | Permission |
| --- | --- | --- |
| /guild setup | Link Discord server to Guild OS guild | Server Admin |
| /rally create | Schedule rally with target, time, troop requirements | R4+ |
| /rally join | RSVP for rally with troop commitment | All members |
| /contribute | Log a contribution (donation, defense, etc.) | All members |
| /stats me | View personal contribution summary | All members |
| /stats guild | View guild-wide analytics summary | R3+ |
| /rep | View reputation profile (self or @user) | All members |
| /endorse @user | Endorse a member for a specific skill | All members |
| /advisor | Ask the AI advisor a strategic question | R3+ |
| /leaderboard | Show top contributors this week/month | All members |
| /screenshot | Upload game screenshot for OCR data extraction | All members |

# 5. Reputation Engine

THE MOAT This is the most important technical system in Guild OS. The reputation engine must be accurate enough that players trust it, transparent enough that they understand it, and portable enough that it becomes their gaming identity. Get this right and you have a network effect that compounds forever. Get this wrong and you have a vanity metric nobody cares about.

## 5.1 Scoring Model

Reputation is calculated as a weighted composite of three sub-scores, each ranging from 0 to 100:

| Dimension | Weight | Inputs | Calculation |
| --- | --- | --- | --- |
| Contribution | 40% | Rally participation, resource donations, defense contributions, event attendance, scout reports | Percentile rank within guild, normalized across games. Accounts for guild size and activity level. |
| Leadership | 30% | Officer tenure, members recruited, events organized, alliance rank held, strategic decisions | Tenure-weighted score. Longer leadership = higher score. Weighted by guild tier and size. |
| Reliability | 30% | Attendance consistency, response time to rallies, shield discipline, RSVP follow-through | Consistency metric. Measures variance — a player who shows up 80% of the time reliably scores higher than one who alternates 100%/0%. |

## 5.2 Anti-Gaming Measures

Reputation systems are only as valuable as they are trustworthy. Multiple layers prevent manipulation:

- Officer Verification: Contributions above a threshold require officer confirmation. Prevents self-reported inflation.

- Peer Endorsement Caps: Each player can endorse the same person for the same skill only once. Endorsements from higher-reputation players carry more weight.

- Decay Function: Inactive periods reduce scores gradually. A player who was active 6 months ago shouldn’t rank the same as someone active today.

- Cross-Validation: When screenshot OCR is available, self-reported data is cross-checked against extracted values. Discrepancies are flagged.

- Anomaly Detection: Statistical outlier detection flags unusual patterns (sudden spike in contributions, mass endorsements from new accounts).

# 6. AI Advisor Architecture

## 6.1 System Design

The AI advisor is built on Claude’s API with game-specific context injection via RAG (Retrieval Augmented Generation). Each query follows this pipeline:

AI ADVISOR PIPELINE 1. USER QUERY └─→ "Should we rally Castle Black or Winterfell?" 2. CONTEXT INJECTION ├─→ Game meta context (current troop balance, recent patches) ├─→ Guild context (member composition, power levels, troop types) ├─→ Target context (enemy alliance stats, known defenses) └─→ Historical context (past rally outcomes vs similar targets) 3. PROMPT CONSTRUCTION └─→ System prompt (game-specific strategic advisor persona) └─→ Structured context + user question 4. CLAUDE API CALL └─→ Claude Sonnet for standard queries (fast, cheap) └─→ Claude Opus for deep strategic analysis (complex) 5. RESPONSE PARSING ├─→ Structured recommendation (target, troop comp, timing) ├─→ Confidence level (high/medium/low) └─→ Supporting reasoning 6. DELIVERY ├─→ Discord embed (formatted for slash command response) └─→ Web dashboard card (rich visualization)

## 6.2 Game Context Store

Each supported game has a maintained knowledge base stored as structured documents:

- Meta Database: Current troop type strengths/weaknesses, gear tier lists, research priorities, building optimization paths. Updated with each game patch.

- Strategy Templates: Common attack/defense strategies, rally compositions for specific targets, event optimization approaches.

- Community Intelligence: Aggregated (anonymized) data from Guild OS users — which compositions win, which targets are hardest, which strategies have the highest success rate.

This context store grows more valuable as more guilds use Guild OS. The AI advisor becomes smarter for everyone as the data pool expands — a classic data network effect.

# 7. Week-by-Week MVP Build Plan

MVP SCOPE The MVP ships in 6 weeks. It includes: Discord bot with basic commands, web dashboard with guild analytics and member stats, reputation scoring v1, event scheduling, and the Alliance Report Card free tool. Everything else is post-MVP.

## Week 1: Foundation

Set up the entire development infrastructure. By end of week, you can deploy a hello-world to production.

| Day | Task | Hours | Phase |
| --- | --- | --- | --- |
| 1 | Initialize Turborepo monorepo, configure TypeScript, ESLint, Prettier | 4h | Build |
| 1 | Set up Supabase project (database, auth, storage) | 2h | Build |
| 2 | Create Next.js app with Tailwind + shadcn/ui, deploy to Vercel | 4h | Build |
| 2 | Set up Drizzle ORM, connect to Supabase, first migration | 3h | Build |
| 3 | Implement core database schema (users, guilds, guild_members) | 4h | Build |
| 3 | Set up Discord OAuth flow in Supabase Auth | 3h | Build |
| 4 | Create Discord bot app, register slash commands, deploy to Railway | 4h | Build |
| 4 | Set up tRPC router with first endpoints (auth, guilds.create) | 3h | Build |
| 5 | Build /guild setup command + guild creation flow on web | 4h | Build |
| 5 | Integration test: Discord OAuth → web dashboard → guild created | 3h | Test |

Week 1 Deliverable: Deployed monorepo with working auth, Discord bot live, guild creation flow end-to-end.

## Week 2: Contribution System

The core data entry and tracking system that everything else depends on.

| Day | Task | Hours | Phase |
| --- | --- | --- | --- |
| 1 | Create contributions table with TimescaleDB hypertable | 3h | Build |
| 1 | Build /contribute slash command (type, value, optional note) | 4h | Build |
| 2 | Build contribution recording API (record, batchRecord, verify) | 4h | Build |
| 2 | Build officer verification flow (Discord buttons + web UI) | 3h | Build |
| 3 | Build member stats dashboard page (charts, trends, breakdown) | 5h | Build |
| 3-4 | Build guild analytics dashboard (aggregate stats, member comparison) | 6h | Build |
| 4 | Build /stats me and /stats guild Discord commands | 3h | Build |
| 5 | Build leaderboard page + /leaderboard Discord command | 4h | Build |
| 5 | Test full contribution flow: Discord → API → dashboard display | 3h | Test |

Week 2 Deliverable: Members can log contributions via Discord, officers can verify, everyone can view stats on the web dashboard.

## Week 3: Reputation & Profiles

The reputation scoring engine and public profile pages — the viral growth mechanism.

| Day | Task | Hours | Phase |
| --- | --- | --- | --- |
| 1 | Implement reputation scoring algorithm in packages/reputation | 5h | Build |
| 1 | Create reputation_scores and reputation_history tables | 2h | Build |
| 2 | Build background job: recalculate reputation scores hourly | 3h | Build |
| 2 | Build endorsement system (endorsements table, /endorse command) | 4h | Build |
| 3 | Build public reputation profile page (/profile/[username]) | 5h | Build |
| 3 | Add SSR + Open Graph meta tags for link preview sharing | 2h | Build |
| 4 | Build /rep Discord command with embedded score card | 3h | Build |
| 4 | Build reputation history chart (score over time, per dimension) | 3h | Build |
| 5 | Build Alliance Report Card (free tool — first guerrilla marketing piece) | 5h | Ship |

Week 3 Deliverable: Reputation scores calculated and displayed. Public profiles shareable with Open Graph previews. Alliance Report Card tool live.

## Week 4: Events & Coordination

Rally scheduling, KvK coordination, and event management tools.

| Day | Task | Hours | Phase |
| --- | --- | --- | --- |
| 1 | Create events and event_signups tables + API endpoints | 4h | Build |
| 1 | Build /rally create Discord command with time/target/requirements | 3h | Build |
| 2 | Build /rally join with troop commitment input | 3h | Build |
| 2 | Build event dashboard page (upcoming, active, past events) | 4h | Build |
| 3 | Build event detail view (signups, troop composition chart, gaps) | 5h | Build |
| 3-4 | Build real-time notifications (Pusher: rally alerts, signup updates) | 4h | Build |
| 4 | Build timezone-aware scheduling with member timezone detection | 3h | Build |
| 5 | Build post-event summary generation (auto-calculate participation stats) | 4h | Build |
| 5 | Test full rally lifecycle: create → signup → execute → summary | 2h | Test |

Week 4 Deliverable: Full event lifecycle working. Rally creation, RSVP, real-time updates, post-event summaries.

## Week 5: AI Advisor + Screenshot OCR

The intelligence layer that makes Guild OS uniquely valuable.

| Day | Task | Hours | Phase |
| --- | --- | --- | --- |
| 1 | Build AI service layer (packages/ai) with Claude API integration | 4h | Build |
| 1 | Write GOTC-specific system prompts and context templates | 3h | Design |
| 2 | Build /advisor Discord command with context injection | 4h | Build |
| 2 | Build AI advisor web chat interface on dashboard | 4h | Build |
| 3 | Build screenshot upload + Claude Vision OCR for game data extraction | 5h | Build |
| 3 | Build /screenshot Discord command (upload image, extract stats) | 3h | Build |
| 4 | Build Rally Calculator free tool (troop composition optimizer) | 5h | Ship |
| 5 | Rate limiting, usage tracking, tier-based query caps | 3h | Build |
| 5 | Test AI advisor accuracy with real GOTC scenarios | 3h | Test |

Week 5 Deliverable: AI advisor answering strategic questions. Screenshot OCR extracting game data. Rally Calculator free tool launched.

## Week 6: Polish, Payments, Launch

Final MVP polish, Stripe integration, landing page, and public launch.

| Day | Task | Hours | Phase |
| --- | --- | --- | --- |
| 1 | Integrate Stripe: subscription tiers, checkout, billing portal | 5h | Build |
| 1 | Build pricing page + upgrade flow in dashboard | 3h | Build |
| 2 | Build landing page (hero, features, social proof, CTA) | 5h | Build |
| 2 | Add PWA manifest + service worker for mobile install | 2h | Build |
| 3 | Full end-to-end testing: new user signup → guild → features | 4h | Test |
| 3 | Performance optimization, error handling, edge cases | 3h | Test |
| 4 | Set up monitoring (Sentry errors, Vercel analytics, Supabase metrics) | 3h | Build |
| 4 | Write documentation, onboarding guide, ambassador materials | 4h | Ship |
| 5 | LAUNCH: Deploy, announce to ambassadors, post to communities | ALL DAY | Ship |

Week 6 Deliverable: Guild OS MVP is live. Discord bot installable. Web dashboard accessible. Payment processing active. Ambassadors onboarding their alliances.

# 8. Post-MVP Technical Roadmap

After the 6-week MVP launch, development shifts from building core features to expanding game support, deepening analytics, and adding platform features.

## Months 2–3: Depth

| Feature | Technical Scope | Priority |
| --- | --- | --- |
| Advanced Analytics | Recharts dashboards, CSV export, custom date ranges, comparative metrics | P0 |
| Notification System | Email digest (Resend), Discord DM alerts, push notifications via PWA | P0 |
| Guild Settings Panel | Configurable contribution types, custom roles, thresholds, notification prefs | P1 |
| Member Onboarding Flow | Guided setup: link game profile, join guild, first contribution, install Discord bot | P1 |
| Reputation Passport Tool | Public standalone tool (guerrilla marketing item #3) | P1 |

## Months 4–6: Expansion

| Feature | Technical Scope | Priority |
| --- | --- | --- |
| Rise of Kingdoms Support | Game-specific schemas, ROK meta knowledge base, adapted AI prompts | P0 |
| Cross-Game Reputation | Unified scoring across games, game-weighted aggregation, global profile | P0 |
| Diplomacy v1 | NAP agreements table, inter-guild messaging, relationship graph | P1 |
| Stripe Billing v2 | Usage-based pricing for AI queries, individual reputation premium tier | P1 |
| Public API (v1) | REST API for community developers. API keys, rate limits, documentation. | P2 |

## Months 7–12: Platform

| Feature | Technical Scope | Priority |
| --- | --- | --- |
| Native Mobile App | React Native (shared components with web). iOS + Android. Push notifications. | P0 |
| Recruitment Marketplace | Player search by reputation, guild recruitment posts, application flow | P0 |
| Lords Mobile + EVE Support | Additional game schemas, meta databases, AI context stores | P1 |
| Tournament Platform | Bracket generation, match tracking, prize distribution, spectator view | P1 |
| Voice Channels (Game-Aware) | WebRTC via LiveKit. Auto-rooms for events, recording, AI summaries. | P2 |
| Data Insights API (B2B) | Anonymized aggregate analytics for game publishers. Partnership API. | P2 |

# 9. Infrastructure & Cost Estimates

## 9.1 Month 1 (MVP Launch)

| Service | Tier | Monthly Cost |
| --- | --- | --- |
| Vercel (web hosting) | Pro ($20/mo) | $20 |
| Supabase (DB + Auth) | Pro ($25/mo) | $25 |
| Railway (Discord bot) | Starter ($5/mo) | $5 |
| Upstash Redis | Pay-as-you-go | $5–$10 |
| Cloudflare R2 (storage) | Free tier (10GB) | $0 |
| Claude API (AI advisor) | Pay-per-token | $50–$200 |
| Pusher (real-time) | Starter (free) | $0 |
| Resend (email) | Free tier | $0 |
| Sentry (monitoring) | Developer (free) | $0 |
| Domain + DNS | Cloudflare | $12/yr |
| TOTAL |  | ~$106–$260/mo |

Total infrastructure cost at launch is under $300/month. This scales linearly with users — Supabase and Vercel pricing is usage-based. At 10,000 users, expect $500–$800/month. At 100,000 users, expect $2,000–$4,000/month. The AI advisor is the largest variable cost, controlled by query caps per tier.

## 9.2 Scaling Thresholds

| Users | Infra Change | Est. Monthly Cost | Revenue Coverage |
| --- | --- | --- | --- |
| 0–1K | MVP stack as-is | $100–$300 | Covered by 5–10 Pro subs |
| 1K–10K | Supabase scale, Redis upgrade | $500–$800 | Covered by 30–50 Pro subs |
| 10K–50K | Dedicated DB, CDN, queue system | $2K–$4K | Covered by 100+ Pro subs |
| 50K–100K | Multi-region, read replicas, edge cache | $4K–$8K | Covered by revenue at scale |

# 10. MVP Launch Checklist

## Pre-Launch (Week 6, Days 1–4)

- All core features deployed to production and smoke-tested

- Stripe subscriptions tested with real cards (test mode)

- Discord bot listed on top.gg with description and invite link

- Landing page live with clear value prop, feature screenshots, and CTA

- Ambassador Discord server set up with onboarding materials

- Alliance Report Card and Rally Calculator free tools live

- Email capture form working with welcome sequence in Resend

- Sentry error monitoring active on all services

- Supabase Row Level Security policies verified

- Rate limiting active on API and AI advisor endpoints

## Launch Day (Week 6, Day 5)

- Deploy final production build to Vercel + Railway

- Send launch announcement to ambassador Discord

- Post to r/GameOfThronesConquest, r/RiseOfKingdoms, r/LordsMobile

- Share Alliance Report Card in 10+ GOTC Discord servers

- DM top 20 GOTC content creators with personal invite

- Monitor error rates, API performance, bot uptime for 12 hours

- Respond to every support question within 1 hour

## Post-Launch (Week 7)

- Daily check: new guild signups, active users, error rates

- Interview first 5 guild leaders for feedback (15 min calls)

- Prioritize bug fixes and UX friction points

- Begin weekly Alliance Intelligence newsletter

- Track and share early reputation profiles on social media

END OF DOCUMENT

Guild OS — Technical Roadmap v1.0 — February 2026